## Permits To Open Dates
Project ID | Project Phase | Address | City | State | Landlord Plan Approval | Building Layout Milk/Shot Side | DD Kickoff | Design Kickoff | Permit Submission | Permit Approval Date | Out To Bid Date | Bid Due Date | General Contractor | Construction Contract Status | Construction Start | Building Drop Date | Certificate of Occupancy Date | Open Date | Construction Time | Marketing Trigger | Notes for Corporate | Building Vendor | Region | DRR
RSH-00053 | Open | 685 Cortez Rd. W. | Bradenton | FL | Approved | Milk |  |  | 2023-12-21 08:00 | 2025-01-27 17:00 |  |  | RNR | Executed Contract | 2025-03-24 08:00 | 2025-05-21 17:00 | 2026-01-07 17:00 | 2026-01-19 17:00 | 290 | 2026-01-12 | sign permit CO? | National Modular | FLSW | FL
RSH-00060 | Open | 5530 SE Abshier Blvd | Belleview | FL | Approved | Shot |  |  | 2024-12-09 08:00 | 2025-07-18 17:00 | 2025-06-09 | 2025-07-03 | CCS | Executed Contract | 2025-07-07 08:00 | 2025-09-17 17:00 | 2025-12-23 17:00 | 2026-01-19 17:00 | 170 | 2026-01-12 | Full CO 1/13 | National Modular | FLSW | FL
RSH-00070 | Open | 945 E Main St. | Weatherford | OK | 8/20 approved via email | Shot | 2025-03-19 08:00 |  | 2025-05-27 08:00 | 2025-07-09 17:00 | 2025-04-22 | 2025-05-12 | Prestige | Executed Contract | 2025-09-03 08:00 | 2025-10-28 17:00 | 2025-12-24 17:00 | 2026-01-19 17:00 | 113 | 2026-01-12 | bollards blocking lanes - GC to correct | CTAR | OKC | OKC
RSH-00073 | Open | 9281 N May Ave | Oklahoma City | OK | Plans have been sent. Approval pending. | Shot | 2024-12-16 08:00 |  | 2025-03-24 08:00 | 2025-07-08 17:00 | 2025-05-12 | 2025-06-16 | Prestige | Executed Contract | 2025-08-27 08:00 | 2025-09-24 17:00 | 2026-01-09 17:00 | 2026-01-26 17:00 | 136 | 2026-01-19 | TCO to operate tracking for 1/7. Guardrails installed as of 1/23. GC to call finals on 2/5 Tracking 2/6 for full CO. | CTAR | OKC | OKC
RSH-00085 | Open | 403 W US HWY 82 | Gainesville | TX | pending (RS) | Shot | 2025-02-06 08:00 |  | 2025-04-15 08:00 | 2025-09-05 17:00 | 2025-04-28 | 2025-06-13 | D&C | Executed Contract |  | 2025-11-04 17:00 | 2025-12-23 17:00 | 2026-01-26 17:00 | 100 | 2026-01-19 |  | CTAR | C. TX | WTX
RSH-00093 | Open | 6403 W Hwy 158 | Midland | TX | Full Plans Approved | Shot | 2025-06-06 08:00 |  | 2025-07-29 08:00 | 2025-09-05 17:00 | 2025-08-01 | 2025-09-05 | D&C | Executed Contract | 2025-10-10 08:00 | 2025-11-19 17:00 | 2026-01-13 17:00 | 2026-01-26 17:00 | 96 | 2026-01-19 | TCO pending ADA sidewalk correction (expires 2/12) | CTAR | W. TX | WTX
RSH-00080 | Open | 300 E Nine Mile | Pensacola | FL | Site plan = approved Full Plans = approved | Milk | 2024-12-17 08:00 |  | 2025-04-25 08:00 | 2025-09-19 17:00 | 2025-06-20 | 2025-07-25 | BJD | Executed Contract | 2025-09-22 08:00 | 2025-11-07 17:00 | 2026-01-15 17:00 | 2026-02-09 17:00 | 116 | 2026-02-02 | Full CO in hand | National Modular | FLPH | FL
RSH-00054 | Open | 5787 Manatee Ave W | Bradenton | FL | Approved | Milk |  |  | 2024-05-20 08:00 | 2025-05-23 17:00 | 2025-04-28 | 2025-06-06 | RNR | Executed Contract | 2025-05-28 08:00 | 2025-06-25 17:00 | 2026-01-30 17:00 | 2026-02-23 17:00 | 248 | 2026-02-16 |  | National Modular | FLSW | FL
RSH-00074 | Open | 1321 Commercial Way | Spring Hill | FL | Plan Approval Letter signed 5/9/25 | Milk |  |  | 2024-12-23 08:00 | 2025-09-26 17:00 | 2025-05-12 | 2025-06-16 | BJD | Executed Contract | 2025-10-16 08:00 | 2025-11-12 17:00 | 2026-02-16 17:00 | 2026-03-09 17:00 | 124 | 2026-03-02 | TCO to operate 2/23. Processing AB Cert for final CO | National Modular | FLSW | FL
RSH-00090 | Open | 2304 N Main St | Belton | TX | Approved | Shot | 2024-11-26 08:00 |  | 2025-06-12 08:00 | 2025-08-15 17:00 | 2025-07-09 | 2025-08-11 | D&C | Executed Contract | 2025-10-23 08:00 | 2025-11-21 17:00 | 2026-02-20 17:00 | 2026-03-09 17:00 | 121 | 2026-03-02 |  | CTAR | C. TX | CTX
RSH-00075 | Open | 1211 W Henderson St. | Cleburne | TX | Full plans approved | Shot |  |  | 2024-12-20 08:00 | 2025-09-05 17:00 | 2025-04-08 | 2025-05-12 | Burd | Executed Contract | 2025-11-03 08:00 | 2025-12-10 17:00 | 2026-03-10 17:00 | 2026-03-30 17:00 | 128 | 2026-03-23 | Canopies coming 2/13 (moved to 3/5). Pocket door/wall needs to be added for health (need to start this by 3/2 to CO 3/13) | CTAR | C. TX | CTX
RSH-00066 | Open | 1050 N Hobart St | Pampa | TX | Pending - need to confirm need | Shot | 2025-06-11 08:00 |  | 2025-07-09 08:00 | 2025-07-29 17:00 | 2025-06-13 | 2025-07-11 | Burd | Executed Contract | 2025-10-20 08:00 |  | 2026-03-10 17:00 | 2026-03-30 17:00 | 142 | 2026-03-23 | Full CO coming 3/11 | Retrofit | W. TX | WTX
RSH-00082 | Open | 3617 Classen Blvd | Norman | OK | sent full plans on 7/23. Comments recvd from LL | Milk | 2025-03-26 08:00 |  | 2025-07-21 08:00 | 2025-09-05 17:00 | 2025-07-23 | 2025-08-18 | Tatco | Executed Contract | 2025-12-01 08:00 | 2026-03-04 17:00 | 2026-03-27 17:00 | 2026-04-13 17:00 | 117 | 2026-04-06 | S&T CO 3/27. tracking full TCO 4/1 (raise FH for perm. CO). porkchop for WM = done. | CTAR | OKC | WTX
RSH-00068 | Open | 1540 N Valley Mills Drive | Waco | TX | Pending | Milk |  |  | 2025-02-27 08:00 | 2025-05-23 17:00 | 2025-07-29 | 2025-08-18 | D&C | Executed Contract | 2025-11-03 08:00 | 2025-12-03 17:00 | 2026-03-27 17:00 | 2026-04-13 17:00 | 145 | 2026-04-06 | TCO to stock 3/23. Full CO on 3/27 per GC | CTAR | C. TX | CTX
RSH-00097 | 7. Construction Phase | 2105 MLK Blvd | Panama City | FL | Approved 08/15/25 | Shot | 2025-01-13 08:00 |  | 2025-05-21 08:00 | 2025-10-31 17:00 | 2025-08-25 | 2025-09-19 | BJD | Executed Contract | 2025-11-19 08:00 | 2026-03-06 17:00 | 2026-04-20 17:00 | 2026-05-04 17:00 | 150 | 2026-04-27 | water and sewer and tied . elec meter installed 3/24. Paving 4/2 . Target TCO for 4/2. Full CO by 4/8 | National Modular | FLPH | FL
RSH-00096 | 7. Construction Phase | 6518 NW Cache Road | Lawton | OK | RS Approved 8/21 | Milk | 2025-03-31 08:00 |  | 2025-07-02 08:00 | 2025-10-08 17:00 | 2025-07-28 | 2025-08-29 | Tatco | Executed Contract | 2026-02-02 08:00 | 2026-03-19 17:00 | 2026-04-29 17:00 | 2026-05-18 17:00 | 89 | 2026-05-11 | water taps done. MEP's & Final by 4/24 . signage - LL & PID confirmed we can re-use old. | CTAR | OKC | WTX
RSH-00091 | 7. Construction Phase | 3008 W Stan Schlueter Loop | Killeen | TX | pending (RS) | Shot |  |  | 2025-07-21 08:00 | 2026-02-05 17:00 | 2025-07-25 | 2025-08-22 | D&C | Executed Contract | 2026-02-18 08:00 | 2026-03-25 17:00 | 2026-04-29 17:00 | 2026-05-18 17:00 | 73 | 2026-05-11 | Shooting for (T)CO by 4/24. | CTAR | C. TX | CTX
RSH-00101 | 7. Construction Phase | 1707 S Valley Mills Dr | Beverly Hills | TX | Approved | Milk | 2025-08-11 08:00 |  | 2025-11-03 08:00 | 2026-02-06 17:00 | 2025-11-14 | 2025-12-12 | D&C | Executed Contract | 2026-02-23 08:00 | 2026-04-01 17:00 | 2026-04-29 17:00 | 2026-05-25 17:00 | 68 | 2026-05-18 | Shooting for (T)CO by 4/24. | CTAR | C. TX | CTX
RSH-00095 | 7. Construction Phase | 1420 Ohio Avenue | Lynn Haven | FL | Approved | Shot |  |  | 2025-03-14 08:00 | 2026-01-02 17:00 | No | Mixed Use |  | Received | 2026-01-22 08:00 | 2026-02-18 17:00 | 2026-05-15 17:00 | 2026-06-01 17:00 | 0.48 | 2026-05-25 | Nichia for muffin top. CO pending soft soil removal | Jack Kurz | FLPH | FL
RSH-00081 | 7. Construction Phase | 490 Mary Esther Blvd. | Mary Esther | FL | Full Plans = Pending | Shot | 2025-03-14 08:00 |  | 2025-07-10 08:00 | 2026-01-02 17:00 | 2025-09-22 | 2025-10-24 | Fulcrum | Executed Contract | 2026-01-26 08:00 | 2026-02-26 17:00 | 2026-05-15 17:00 | 2026-06-01 17:00 | 110 | 2026-05-25 | water and power on. storm/sewer conflict | National Modular | FLPH | FL
RSH-00071 | 7. Construction Phase | 1194 S. Broad St | Brooksville | FL | Full plans approved - 2/10/2025 | Shot |  |  | 2024-11-15 08:00 | 2025-12-01 17:00 | 2025-06-17 | 2025-07-09 | RNR | Executed Contract | 2026-01-12 08:00 | 2026-03-11 17:00 | 2026-05-22 17:00 | 2026-06-08 17:00 | 131 | 2026-06-01 | GC confirmed CO target of 5/22 | National Modular | FLSW | FL
RSH-00079 | 7. Construction Phase | 833 W. Edmond Rd. | Edmond | OK | Approved - 8/14 | Shot |  |  | 2024-10-29 08:00 | 2025-12-01 17:00 | 2025-03-04 | 2025-03-31 | Prestige | Executed Contract |  | 2026-03-17 17:00 | 2026-05-29 17:00 | 2026-06-15 17:00 | 103 | 2026-06-08 | Electric line relocation by City and 7Crew = done | CTAR | OKC | OKC
RSH-00069 | 7. Construction Phase | 801 Beal Pkwy N | Fort Walton Beach | FL | Approved - 6/2 | Shot |  |  | 2025-01-28 08:00 | 2025-10-10 17:00 | 2025-06-02 | 2025-06-23 | RNR | Executed Contract | 2025-12-17 08:00 | 2026-03-04 17:00 | 2026-06-05 17:00 | 2026-06-22 17:00 | 171 | 2026-06-15 | Need GC/County to verify CO. GC tracking Building final 5/13 and CO 6/5 | National Modular | FLPH | FL
RSH-00116 | 7. Construction Phase | 210 23rd St | Canyon | TX | Full Plans = approval letter received 2/18 | Shot | 2025-08-12 08:00 |  | 2025-09-15 08:00 | 2026-03-18 17:00 | 2025-09-26 | 2025-10-31 | Burd | Executed Contract | 2026-03-02 08:00 | 2026-04-15 17:00 | 2026-06-05 17:00 | 2026-06-22 17:00 | 96 | 2026-06-15 | confirm CO date with GC. water tapped. Sewer and Gt go in week of 4/24 | CTAR | W. TX | WTX
RSH-00109 | 7. Construction Phase | 2415 S Country Club Rd | El Reno | OK | Full Plans = approved 2/4 | Shot | 2025-08-12 08:00 |  | 2025-11-06 08:00 | 2026-01-21 17:00 | 2025-11-14 | 2025-12-12 | VBC | Executed Contract | 2026-02-23 08:00 | 2026-05-26 17:00 | 2026-06-26 17:00 | 2026-07-13 17:00 | 110 | 2026-07-06 | UES out for testing on 4/21/. BD of 5/26 to be confirmed with CTAR | CTAR | OKC | OKC
RSH-00106 | 7. Construction Phase | 12902 Indiana Ave | Lubbock | TX | Site plan = approved Full Plans = approved | Shot | 2025-08-12 08:00 |  | 2025-11-12 08:00 | 2026-04-09 17:00 | 2026-01-21 | 2026-02-13 | Walker Co. | Executed Contract | 2026-04-08 08:00 | 2026-04-24 17:00 | 2026-07-08 17:00 | 2026-07-27 17:00 | 92 | 2026-07-20 |  | CTAR | W. TX | WTX
RSH-00123 | 7. Construction Phase | 108 Sequoyah Ln | Altus | OK | Full plans = approved | Shot | 2025-09-08 08:00 |  | 2026-01-21 08:00 | 2026-02-20 17:00 | 2026-01-21 | 2026-02-13 | Walker Co. | Executed Contract | 2026-04-06 08:00 | 2026-04-21 17:00 | 2026-07-17 17:00 | 2026-08-03 17:00 | 103 | 2026-07-27 | GC reporting CO of 5/29 | CTAR | OKC | WTX
RSH-00078 | 7. Construction Phase | 1937 US 19 Hwy | Holiday | FL | pending | Shot |  | 2024-10-30 08:00 | 2024-10-31 08:00 | 2026-02-17 17:00 | 2025-12-23 | 2026-01-16 | Tatco (FL) | Executed Contract | 2026-04-06 08:00 | 2026-04-29 17:00 | 2026-07-24 17:00 | 2026-08-10 17:00 | 110 | 2026-08-03 | Site Plan approved 12/2. Site Permit Placard issues 2.17. All permits in hand on 3/25 | National Modular | FLSW | FL
RSH-00089 | 7. Construction Phase | 401 Gulf Breeze Pkwy. | Gulf Breeze | FL | pending (RS) | Milk |  |  | 2024-11-06 08:00 | 2025-08-27 17:00 | 2025-05-29 | 2025-07-08 | RNR | Executed Contract | 2026-01-05 08:00 |  | 2026-07-24 17:00 | 2026-08-10 17:00 | 201 | 2026-08-03 | GC building final target = 7/16 & CO target date = 8/14 | Stick Build | FLPH | FL
RSH-00114 | 7. Construction Phase | 8106 N Davis Hwy | Pensacola | FL | Approved | Shot | 2025-06-18 08:00 |  | 2025-11-14 08:00 | 2026-02-25 17:00 | 2026-02-09 | 2026-02-27 | Fulcrum | Executed Contract | 2026-04-07 08:00 | 2026-06-03 17:00 | 2026-07-24 17:00 | 2026-08-10 17:00 | 109 | 2026-08-03 |  | National Modular | FLPH | FL
RSH-00110 | 7. Construction Phase | 955 US-377 | Granbury | TX | Full Plans = approval letter received 3/26 | Shot | 2025-08-12 08:00 |  | 2025-11-26 08:00 | 2026-04-02 17:00 | 2025-12-10 | 2026-01-12 | VBC | Executed Contract | 2026-04-20 08:00 | 2026-05-20 17:00 | 2026-07-24 17:00 | 2026-08-10 17:00 | 97 | 2026-08-03 |  | CTAR | C. TX | CTX
RSH-00133 | 6. Permitting Phase | 2917 SW 104th St. | Oklahoma City | OK | 4/10 - Approved | Milk | 2025-09-08 08:00 |  | 2025-12-03 08:00 | 2026-04-08 17:00 | 2026-02-20 | 2026-03-05 | Prestige | Executed Contract | 2026-04-27 08:00 | 2026-05-27 17:00 | 2026-07-24 17:00 | 2026-08-10 17:00 | 96 | 2026-08-03 | Permit expected 4/7. Need GC to verify construction schedule | CTAR | OKC | OKC
RSH-00092 | 7. Construction Phase | 9101 College Pkwy. | Fort Myers | FL | Approved | Shot |  |  | 2024-11-21 08:00 | 2026-04-17 17:00 | 2025-12-03 | 2025-12-22 | BJD | Executed Contract | 2026-04-08 08:00 | 2026-05-20 17:00 | 2026-07-31 17:00 | 2026-08-17 17:00 | 115 | 2026-08-10 | Owl is gone. SWPPP to be inspected 4/23-24. BD of 5/20 to be confirmed with NM | National Modular | FLSW | FL
RSH-00087 | 6. Permitting Phase | 1603 3rd St | Winter Haven | FL | "Site Plan = in lease. should be ok Full Plans Pending" | Shot |  |  | 2025-05-02 08:00 | 2026-04-17 17:00 | 2025-09-05 | 2025-10-03 | Tatco (FL) | Bid sent to Legal / Negotiating Contract - Legal | 2026-04-27 08:00 | 2026-06-03 17:00 | 2026-08-28 17:00 | 2026-09-14 17:00 | 124 | 2026-09-07 | Permits delayed for FDOT Drainage comment. Need to verify property boundary | Valiant | FLSW | FL
RSH-00104 | 6. Permitting Phase | 13500 N Rockwell Ave | OKC | OK | "Site plan = pending |  |  |  | 2026-03-25 08:00 | 2026-08-21 17:00 | 2026-04-24 | 2026-05-15 | Citadel | Out to Bid | 2026-05-27 08:00 |  | 2026-09-02 17:00 | 2026-09-21 17:00 | 96 | 2026-09-14 |  | CTAR | OKC | OKC
RSH-00094 | 7. Construction Phase | 4102 Cleveland Ave | Fort Myers | FL | Site plan = Approved Full Plans = Approved | Shot |  |  | 2025-04-15 08:00 | 2026-04-10 17:00 | 2025-10-24 | 2025-11-21 | BJD | Bid sent to Legal / Negotiating Contract - Legal | 2026-04-20 08:00 | 2026-06-03 17:00 | 2026-09-10 17:00 | 2026-09-28 17:00 | 144 | 2026-09-21 |  | Valiant | FLSW | FL
RSH-00102 | 7. Construction Phase | 3700 College Ave | Snyder | TX | Site plan = pending Full Plans = Pending Plan approval signed 4/9/26 | Shot | 2025-08-11 08:00 | 2025-09-05 08:00 | 2025-09-06 08:00 | 2026-04-13 17:00 | 2026-03-17 | 2026-03-30 | Burd | Executed Contract | 2026-04-13 08:00 |  | 2026-09-07 17:00 | 2026-09-28 17:00 | 148 | 2026-09-21 | TXDOT approved 3/16. Oncor needs 4 weeks from KO to move poles. tracking pole move for 4/22 based on 3/25 KO. parking agreement submitted 4/7 | Stick Build | W. TX | WTX
RSH-00084 | 6. Permitting Phase | 1225 Tamiami Trail | Punta Gorda | FL | Approved | Milk |  |  | 2025-03-07 08:00 | 2026-05-22 17:00 | 2025-06-30 | 2025-07-25 | BJD | Negotiating Bid - Jeff | 2026-05-25 08:00 | 2026-07-01 17:00 | 2026-09-10 17:00 | 2026-09-28 17:00 | 102 | 2026-09-21 |  | National Modular | FLSW | FL
RSH-00112 | 6. Permitting Phase | 100 S New Rd | Waco | TX | "Site Plan = pending Full plans = Pending" | Shot | 2025-08-12 08:00 |  | 2026-03-24 08:00 | 2026-06-05 17:00 | 2026-04-08 | 2026-05-15 |  | Out to Bid | 2026-06-22 08:00 | 2026-07-15 17:00 | 2026-09-18 17:00 | 2026-10-05 17:00 | 89 | 2026-09-28 | TXDOT work during opening | CTAR | C. TX | CTX
RSH-00103 | 5. Design Phase | 736 Hewitt Dr | Waco | TX | Full Plans = Pending |  | 2025-08-11 08:00 |  | 2026-05-20 08:00 | 2026-06-26 17:00 | 2026-05-11 | 2026-06-05 | Citadel | Out to Bid | 2026-07-06 08:00 |  | 2026-09-23 17:00 | 2026-10-12 17:00 | 80 | 2026-10-05 | need to confirm submittal date with citadel | Retrofit | C. TX | CTX
RSH-00088 | 6. Permitting Phase | 1201 Homestead Rd N | Lehigh Acres | FL | Site Plan Approved Full plans = Approved 02/2025 | Shot |  |  | 2024-11-08 08:00 | 2026-04-30 17:00 | 2025-11-14 | 2025-12-12 | BJD | Negotiating Bid - Jeff | 2026-05-06 08:00 | 2026-06-03 17:00 | 2026-10-02 17:00 | 2026-10-19 17:00 | 150 | 2026-10-12 | Turn lane required and SWFWMD now required. | National Modular | FLSW | FL
RSH-00086 | 6. Permitting Phase | 3104 SW College Rd | Ocala | FL | pending | Milk | 2024-08-01 08:00 |  | 2024-12-11 08:00 | 2026-05-20 17:00 | 2026-04-07 | 2026-05-08 |  | Out to Bid | 2026-05-25 08:00 | 2026-07-08 17:00 | 2026-10-16 17:00 | 2026-11-02 17:00 | 145 | 2026-10-26 | City has approved site plan and traffic. LL tenant approval could delay CS | National Modular | FLSW | FL
RSH-00229 | 6. Permitting Phase | 4615 Mobile Hwy | Pensacola | FL | Approved 3/6 | Shot | 2025-09-26 08:00 |  | 2026-01-26 08:00 | 2026-05-29 17:00 | 2026-03-18 | 2026-04-10 | Fulcrum | Negotiating Bid - Jeff | 2026-06-15 08:00 | 2026-07-22 17:00 | 2026-10-09 17:00 | 2026-11-02 17:00 | 117 | 2026-10-26 |  | National Modular | FLPH | FL
RSH-00139 | 6. Permitting Phase | 1811 24th Ave NW | Norman | OK |  | Shot | 2025-09-10 08:00 |  | 2026-03-10 08:00 | 2026-06-26 17:00 | 2026-04-14 | 2026-05-18 |  | Out to Bid | 2026-07-06 08:00 | 2026-08-05 17:00 | 2026-10-21 17:00 | 2026-11-02 17:00 | 108 | 2026-10-26 | City fully signed off pending ARB (3rd party review - no hearing) | CTAR | OKC | OKC
RSH-00083 | 6. Permitting Phase | 7236 Northwest Expy | Oklahoma City | OK | pending | Shot | 2024-12-23 08:00 |  | 2025-03-25 08:00 | 2025-07-11 17:00 | 2025-06-06 | 2025-07-02 | Prestige | Bid sent to Legal / Negotiating Contract - Legal | 2026-07-27 08:00 | 2026-09-09 17:00 | 2026-10-23 17:00 | 2026-11-09 17:00 | 89 | 2026-11-02 | Permits expire 7/7/26. Lease - (appraisers to find Fair market value rent). expecting LL lease redlines 4/16 with goal to have leases agreed to by 4/17 |  | OKC | OKC
RSH-00134 | 6. Permitting Phase | 803 NE Alsbury Blvd. | Burleson | TX | TBD |  |  |  | 2026-03-25 08:00 | 2026-07-10 17:00 | 2026-05-08 | 2026-06-05 |  |  | 2026-07-20 08:00 | 2026-08-26 17:00 | 2026-10-23 17:00 | 2026-11-09 17:00 | 96 | 2026-11-02 | Civils ONLY in 3/25 | CTAR | C. TX | CTX
RSH-00180 | 6. Permitting Phase | 2602 50th St. Suite 300 | Lubbock | TX |  | Shot | 2025-11-19 08:00 | 2026-02-11 08:00 | 2026-03-11 08:00 | 2026-07-17 17:00 | 2026-05-22 | 2026-04-14 |  | Out to Bid | 2026-07-13 08:00 | 2026-09-02 17:00 | 2026-10-23 17:00 | 2026-11-09 17:00 | 129 | 2026-11-02 | second round of city review | CTAR | W. TX | WTX
RSH-00077 | 6. Permitting Phase | 160 Mariner Blvd | Spring Hill | FL | "Site Plan = approval Full plans = Pending" | Shot | 2024-09-18 08:00 | 2025-01-01 08:00 | 2025-11-05 08:00 | 2026-06-05 17:00 | 2026-04-17 | 2026-05-15 |  |  | 2026-07-06 08:00 | 2026-10-21 17:00 | 2027-02-05 17:00 | 2026-12-07 17:00 | 215 | 2026-11-30 | Corrected LL Applications on 12/16 (WMD might need clearer version) | National Modular | FLSW | FL
RSH-00113 | 6. Permitting Phase | 1289 S Sumter Blvd | North Port | FL | "Site plan = pending Full Plans = Pending" | Milk | 2025-05-06 08:00 |  | 2025-10-09 08:00 | 2026-08-14 17:00 | 2026-06-01 | 2026-06-26 | BJD | Out to Bid | 2026-08-24 08:00 |  | 2026-11-25 17:00 | 2026-12-07 17:00 | 94 | 2026-11-30 |  | Stick-built | FLSW | FL
RSH-00129 | 6. Permitting Phase | 4111 East US Hwy 377 | Granbury | TX | Site Plan = pending Full plans = Pending |  | 2025-09-10 08:00 |  | 2026-04-01 08:00 | 2026-07-31 17:00 | 2026-04-17 | 2026-05-15 |  |  | 2026-08-10 08:00 | 2026-09-16 17:00 | 2026-11-25 17:00 | 2026-12-07 17:00 | 108 | 2026-11-30 | Parking Variance approved 3/31. LL to deliver pad & utilities in May (MH to confirm) | CTAR | C. TX | CTX
RSH-00149 | 6. Permitting Phase | 1020 E State Hwy 152 Suite 100 | Mustang | OK |  | Shot | 2025-09-08 08:00 |  | 2026-03-27 08:00 | 2026-08-19 17:00 | 2026-04-17 | 2026-05-01 |  |  | 2026-09-07 08:00 |  | 2026-12-11 17:00 | 2027-01-04 17:00 | 96 | 2026-12-28 | 3/27 is civil only submittal. Holding building submit for LL/City comments | Stick Build | OKC | OKC
RSH-00100 | 6. Permitting Phase | 3001 W University Blvd | Odessa | TX | 9/15 - Art Received "Site plan = pending Full Plans = Pending" | Milk | 2025-08-11 08:00 |  | 2026-02-20 08:00 | 2026-08-14 17:00 | 2026-06-01 | 2026-06-26 |  |  | 2026-08-31 08:00 | 2026-09-30 17:00 | 2026-12-09 17:00 | 2027-01-18 17:00 | 101 | 2027-01-11 | Plat is approved. SP submitted late February, review commencing as of plat approval. Lease amendment for SP rights and IP extended signed 4/3. Need REA and parking agreement (tracking 4/9) | CTAR | W. TX | WTX
RSH-00151 | 4. Due Diligence Phase | 3514 E Interstate Drive | Amarillo | TX |  | Shot | 2025-10-08 08:00 | 2026-05-06 08:00 | 2026-05-22 08:00 | 2026-08-21 17:00 |  |  |  |  | 2026-09-07 08:00 | 2026-10-07 17:00 | 2026-12-04 17:00 | 2027-01-18 17:00 | 89 | 2027-01-11 | LL provided Lease redlines 1/28. 7C sent redlines back 2/4. LL reviewing 7C financials and other tenant plans (chick express & title max), legal call on 4/1. LL still owes REA response as of 4/22 | CTAR | W. TX | WTX
RSH-00692 | 4. Due Diligence Phase | 7101 Park Blvd | Pinellas Park | FL |  |  | 2026-03-31 08:00 |  | 2026-07-29 08:00 | 2026-10-02 17:00 |  |  |  |  | 2026-10-26 08:00 | 2026-12-02 17:00 | 2027-01-08 17:00 | 2027-01-25 17:00 | 75 | 2027-01-18 | LL to design and permit all civil/site, 7C to drop building, landscape TBD. LL prelim civils in review at City. | Valiant | FLSW | FL
RSH-00528 | 5. Design Phase | 2401 Henney Rd | Choctaw | OK |  |  | 2026-01-07 08:00 |  | 2026-05-01 08:00 | 2026-09-04 17:00 | 2026-06-19 | 2026-07-17 |  |  | 2026-09-21 08:00 | 2026-11-04 17:00 | 2027-01-13 17:00 | 2027-02-01 17:00 | 115 | 2027-01-25 | LL has to complete lot split and record utility easement before 7C can submit for plans and review. Need to confirm no CLOMR (adds 6 - 9 months) | CTAR | OKC | OKC
RSH-00117 | 6. Permitting Phase | 9305 US-19 | Port Richey | FL | "Site Plan = verbal approved Full plans = Pending" | Shot | 2025-04-23 08:00 |  | 2025-12-17 08:00 | 2026-08-28 17:00 | 2026-04-20 | 2026-05-20 |  |  | 2026-09-14 08:00 | 2026-10-14 17:00 | 2027-02-05 17:00 | 2027-02-22 17:00 | 145 | 2027-02-15 |  | Valiant | FLSW | FL
RSH-00111 | 6. Permitting Phase | 35910 US-27 | Haines City | FL | Site Plan = pending Full plans = Pending | Milk | 2025-07-21 08:00 |  | 2026-04-15 08:00 | 2026-09-04 17:00 |  |  |  |  | 2026-09-21 08:00 | 2026-10-21 17:00 | 2027-02-05 17:00 | 2027-02-22 17:00 | 138 | 2027-02-15 | 12/9 - 7C asking title if LL access/parking is acceptable | Valiant | FLSW | FL
RSH-00146 | 6. Permitting Phase | 7725 Moccasin Wallow Road | Palmetto | FL | Site plan = pending Full Plans = Pending | Shot | 2025-09-26 08:00 |  | 2026-02-23 08:00 | 2026-09-09 17:00 |  |  |  |  | 2026-09-28 08:00 | 2026-09-09 17:00 | 2027-02-12 17:00 | 2027-03-01 17:00 | 138 | 2027-02-22 |  | Valiant | FLSW | FL
RSH-00592 | 4. Due Diligence Phase | 1080 Fort Hood St | Killeen | TX |  |  | 2026-02-11 08:00 | 2026-06-10 08:00 | 2026-07-03 08:00 | 2026-11-06 17:00 |  |  |  |  | 2026-12-02 08:00 | 2027-01-13 17:00 | 2027-04-02 17:00 | 2027-04-19 17:00 | 122 | 2027-04-12 |  | CTAR | C. TX | CTX
RSH-00147 | 6. Permitting Phase | 10581 Colonial Blvd | Fort Myers | FL | Site Plan = pending Full plans = Pending | Shot | 2025-08-22 08:00 |  | 2026-03-24 08:00 | 2026-10-16 17:00 |  |  |  |  | 2026-11-04 08:00 | 2026-12-09 17:00 | 2027-04-02 17:00 | 2027-04-19 17:00 | 150 | 2027-04-12 |  | Valiant | FLSW | FL
RSH-00231 | 6. Permitting Phase | 19017 S Tamiami Trl | Fort Myers | FL | 2/19 = Civils and arch elevations sent | Milk | 2025-09-26 08:00 |  | 2026-03-02 08:00 | 2026-11-13 17:00 |  |  |  |  | 2026-11-30 08:00 | 2027-01-13 17:00 | 2027-04-16 17:00 | 2027-05-03 17:00 | 138 | 2027-04-26 |  | Valiant | FLSW | FL
RSH-00606 | 4. Due Diligence Phase | 2215 N Big Spring St | Midland | TX |  |  | 2026-02-13 08:00 | 2026-06-24 08:00 | 2026-07-10 08:00 | 2026-11-27 17:00 |  |  |  |  | 2026-12-14 08:00 | 2027-01-27 17:00 | 2027-04-16 17:00 | 2027-05-03 17:00 | 124 | 2027-04-26 | PLACEHOLDER DATES | Stick-build | W. TX
RSH-00617 | 5. Design Phase | 390 TX-199 | Springtown | TX |  |  | 2026-01-28 08:00 | 2026-04-17 08:00 | 2026-05-15 08:00 | 2026-11-06 17:00 |  |  |  |  | 2026-12-02 08:00 | 2027-01-06 17:00 | 2027-04-16 17:00 | 2027-05-03 17:00 | 136 | 2027-04-26 | PLACEHOLDER DATES. P&Z hearing for canopy in BS on 4/8 | CTAR | C. TX | WTX
RSH-00273 | 5. Design Phase | 6875 N Church Ave | Mulberry | FL |  | Milk | 2025-09-25 08:00 | 2026-03-18 08:00 | 2026-05-22 08:00 | 2026-11-13 17:00 |  |  |  |  | 2026-11-30 08:00 | 2027-01-06 17:00 | 2027-04-16 17:00 | 2027-05-03 17:00 | 138 | 2027-04-26 | Civil only KO on 3/18. | Valiant | FLSW | FL
RSH-00127 | 5. Design Phase | Covell and Sooner | Edmond | OK |  | Shot | 2025-09-12 08:00 |  | 2026-04-14 08:00 | 2026-12-11 17:00 | 2026-08-14 | 2026-09-11 |  |  | 2027-01-06 08:00 | 2027-02-10 17:00 | 2027-05-07 17:00 | 2027-05-24 17:00 | 122 | 2027-05-17 | Only Rider is outstanding for Lease - target execution is 2/27 | CTAR | OKC | OKC
RSH-00115 | 5. Design Phase | 1159 Missouri Ave N | Largo | FL | "Site Plan = pending Full plans = Pending" | Milk | 2025-05-23 08:00 |  | 2026-05-01 08:00 | 2027-01-06 17:00 |  |  |  |  | 2027-01-25 08:00 | 2027-03-03 17:00 | 2027-05-28 17:00 | 2027-06-14 17:00 | 124 | 2027-06-07 | lease is close. should be signed in next few days (note on 3/18) | Valiant | FLSW | FL
RSH-00266 | 4. Due Diligence Phase | 116 Sebring Square | Sebring | FL |  | Milk | 2025-10-24 08:00 |  | 2026-06-10 08:00 | 2027-01-08 17:00 |  |  |  |  | 2027-02-03 08:00 | 2027-03-10 17:00 | 2027-06-04 17:00 | 2027-06-21 17:00 | 122 | 2027-06-14 | 3/11 DKO is aggressive. 1/28 - LL receives first draft of lease. 7C got LL redlines on 2/10. LL working on legal description. 3/11 is agressive for DKO | Valiant | FLSW | FL
RSH-00205 | 4. Due Diligence Phase | 2159 W 9 Mile Rd | Pensacola | FL |  | Shot | 2025-09-26 08:00 |  | 2026-06-05 08:00 | 2027-01-08 17:00 |  |  |  |  | 2027-01-25 08:00 | 2027-03-10 17:00 | 2027-06-04 17:00 | 2027-06-21 17:00 | 131 | 2027-06-14 | Pause for LOI delays from LL sale and use restriction concerns | National Modular | FLPH | FL
RSH-00211 | 4. Due Diligence Phase | 12720 U.S. Hwy 19 | Hudson | FL |  | Shot | 2025-09-22 08:00 | 2026-05-06 08:00 | 2026-06-05 08:00 | 2027-02-05 17:00 |  |  |  |  | 2027-02-22 08:00 | 2027-03-31 17:00 | 2027-07-02 17:00 | 2027-07-19 17:00 | 131 | 2027-07-12 |  | Valiant | FLSW | FL
RSH-00579 | 4. Due Diligence Phase | 1325 E Oak St | Arcadia | FL |  |  | 2026-02-25 08:00 | 2026-06-26 08:00 | 2026-08-07 08:00 | 2027-02-12 17:00 |  |  |  |  | 2027-03-01 08:00 | 2027-04-01 17:00 | 2027-07-09 17:00 | 2027-07-26 17:00 | 131 | 2027-07-19 | PLACEHOLDER DATES | Valiant | FLSW | FL
RSH-00610 | 4. Due Diligence Phase | 16564 US-331 | Freeport | FL |  |  | 2026-03-25 08:00 |  | 2026-08-07 08:00 | 2027-02-12 17:00 |  |  |  |  | 2027-03-01 08:00 | 2027-04-01 17:00 | 2027-07-09 17:00 | 2027-07-26 17:00 | 131 | 2027-07-19 | PLACEHOLDER DATES | CTAR | FLPH | FL
RSH-00108 | 5. Design Phase | 4801 Cortez Blvd | Bradenton | FL | Site Plan = pending Full plans = Pending | Shot | 2025-08-01 08:00 | 2026-05-06 08:00 | 2026-05-31 08:00 | 2027-02-19 17:00 |  |  |  |  | 2027-03-08 08:00 | 2027-04-07 17:00 | 2027-07-16 17:00 | 2027-08-02 17:00 | 131 | 2027-07-26 | DD KO 2/25 is very aggressive. another lease call on 2/5. | Valiant | FLSW | FL
RSH-00582 | 4. Due Diligence Phase | Cottonwood & Hwy 27 | Davenport | FL |  |  | 2026-01-14 08:00 | 2026-05-20 08:00 | 2026-06-26 08:00 | 2027-02-17 17:00 |  |  |  |  | 2027-03-15 08:00 | 2027-04-14 17:00 | 2027-07-16 17:00 | 2027-08-02 17:00 | 124 | 2027-07-26 | PLACEHOLDER DATES | Valiant | FLSW | FL
RSH-00584 | 4. Due Diligence Phase | 1405 W Buckingham Rd | Garland | TX |  |  | 2026-02-25 08:00 |  | 2026-08-07 08:00 | 2027-05-07 17:00 |  |  |  |  | 2027-05-31 08:00 | 2027-07-07 17:00 | 2027-08-13 17:00 | 2027-08-30 17:00 | 75 | 2027-08-23 | PLACEHOLDER DATES. Need 6-9 months for SUP | CTAR | C. TX | Dallas
RSH-00099 | 5. Design Phase | NWC of Alf Coleman & Hwy 98 | Panama City Beach | FL | "Site Plan = pending (RS) Full plans = Pending" | Shot | 2025-04-01 08:00 |  | 2026-05-01 08:00 | 2027-01-15 17:00 |  |  |  |  | 2027-02-01 08:00 | 2027-04-16 17:00 | 2027-08-13 17:00 | 2027-08-30 17:00 | 194 | 2027-08-23 | coordinate LL Delivery - KM & KB | National Modular | FLPH | FL
RSH-00213 | 4. Due Diligence Phase | 1048 W HWY 67 | Alvarado | TX | [10 empty] | 2027-04-19 08:00 | 2027-05-19 17:00 | 2027-08-20 17:00 | 2027-09-06 17:00 | #INVALID DATA TYPE | 2027-08-30 |  |  | C. TX | CTX
RSH-00596 | 4. Due Diligence Phase | 6051 Skillman St | Dallas | TX |  |  | 2026-01-07 08:00 |  | 2026-07-17 08:00 | 2027-04-16 17:00 |  |  |  |  | 2027-05-10 08:00 | 2027-06-16 17:00 | 2027-09-03 17:00 | 2027-09-20 17:00 | 117 | 2027-09-13 | LL LOI comments back as of 1/28. &C send back 2/6. Need utility easement agreement with smoothie king (3-6 month). DIR = Dev Impact Review (PD mod - 6-9 months) | CTAR | C. TX | Dallas
RSH-00601 | 4. Due Diligence Phase | 1738 N Town E Blvd | Mesquite | TX |  |  | 2026-03-11 08:00 |  | 2026-09-03 08:00 | 2027-03-12 17:00 |  |  |  |  | 2027-05-03 08:00 | 2027-06-09 17:00 | 2027-09-03 17:00 | 2027-09-20 17:00 |  | 2027-09-13 |  |  | C. TX | Dallas
RSH-00235 | 3. LOI Negotiations | 2210 Del Prado Blvd S | Cape Coral | FL |  |  | 2026-04-08 08:00 |  | 2026-07-24 08:00 | 2027-03-26 17:00 |  |  |  |  | 2027-04-19 08:00 | 2027-06-02 17:00 | 2027-09-17 17:00 | 2027-10-04 17:00 | 152 | 2027-09-27 |  |  | FLSW | FL
RSH-00575 | 4. Due Diligence Phase | 2805 S 14th St | Abilene | TX |  |  | 2026-03-25 08:00 |  | 2026-08-28 08:00 | 2027-04-30 17:00 |  |  |  |  | 2027-05-17 08:00 | 2027-06-21 17:00 | 2027-10-01 17:00 | 2027-10-18 17:00 | 138 | 2027-10-11 | PLACEHOLDER DATES |  | W. TX | WTX
RSH-00208 | 4. Due Diligence Phase | 2511 Thomas Dr | Panama City Beach | FL |  | Milk | 2025-11-05 08:00 |  | 2026-09-04 08:00 | 2027-05-14 17:00 |  |  |  |  | 2027-05-31 08:00 | 2026-10-28 17:00 | 2027-10-01 17:00 | 2027-10-18 17:00 | 124 | 2027-10-11 |  | National Modular | FLPH | FL
RSH-00126 | 4. Due Diligence Phase | 3900 E 15th St | Edmond | OK |  |  | 2026-03-25 08:00 |  | 2026-08-28 08:00 | 2027-04-30 17:00 |  |  |  |  | 2027-05-17 08:00 | 2027-06-21 17:00 | 2027-10-01 17:00 | 2027-10-18 17:00 | 138 | 2027-10-11 | PLACEHOLDER DATES |  | OKC | OKC
RSH-00233 | 3. LOI Negotiations | 15201 N Cleveland Ave | Fort Myers | FL |  |  | 2026-01-28 08:00 |  | 2026-06-29 08:00 | 2027-05-28 17:00 |  |  |  |  | 2027-06-14 08:00 | 2027-07-14 17:00 | 2027-10-14 17:00 | 2027-11-01 17:00 | 123 | 2027-10-25 | PLACEHOLDER DATES | Valiant | FLSW | FL
RSH-00622 | 4. Due Diligence Phase | 1751 66th St N | St. Petersburg | FL |  |  | 2026-02-11 08:00 |  | 2026-07-24 08:00 | 2027-04-30 17:00 |  |  |  |  | 2027-05-17 08:00 | 2027-07-14 17:00 | 2027-10-15 17:00 | 2027-11-01 17:00 | 152 | 2027-10-25 | PLACEHOLDER DATES. Lease draft went to LL around 4/1 and awaing LL reply | Valiant | FLSW | FL
RSH-00217 | 4. Due Diligence Phase | 7603 Seminole Blvd | Seminole | FL |  |  | 2026-02-25 08:00 |  | 2026-08-07 08:00 | 2027-04-30 17:00 |  |  |  |  | 2027-05-17 08:00 | 2027-06-23 17:00 | 2027-10-22 17:00 | 2027-11-08 17:00 | 159 | 2027-11-01 | PLACEHOLDER DATES | Valiant | FLSW | FL
RSH-00634 | 4. Due Diligence Phase | 983 US-98 | Destin | FL |  |  | 2026-03-25 08:00 |  | 2026-09-04 08:00 | 2027-05-07 17:00 |  |  |  |  | 2027-05-24 08:00 | 2027-07-07 17:00 | 2027-10-22 17:00 | 2027-11-08 17:00 | 152 | 2027-11-01 | PLACEHOLDER DATES |  | FLPH | FL
RSH-00621 | 4. Due Diligence Phase | 2801 James L Redman Pkwy | Plant City | FL |  |  | 2026-04-08 08:00 |  | 2026-09-11 08:00 | 2027-05-28 17:00 |  |  |  |  | 2027-06-21 08:00 | 2027-07-21 17:00 | 2027-10-29 17:00 | 2027-11-15 17:00 | 131 | 2027-11-08 | PLACEHOLDER DATES |  | FLSW | FL
RSH-00620 | 4. Due Diligence Phase | 906 W University Dr | Denton | TX |  |  | 2026-04-08 08:00 |  | 2026-10-09 08:00 | 2027-04-30 17:00 |  |  | Walker Co. |  | 2027-05-17 08:00 |  | 2027-10-29 17:00 | 2027-11-15 17:00 | 166 | 2027-11-08 | PLACEHOLDER DATES | Retrofit | C. TX | WTX
RSH-00656 | 4. Due Diligence Phase | 2317 Gunn Hwy | Odessa | FL |  |  | 2026-04-08 08:00 |  | 2026-09-11 08:00 | 2027-05-28 17:00 |  |  |  |  | 2027-06-21 08:00 | 2027-07-21 17:00 | 2027-10-29 17:00 | 2027-11-15 17:00 | 131 | 2027-11-08 | PLACEHOLDER DATES |  | FLSW | FL
RSH-00119 | 4. Due Diligence Phase | SWC of Nine Mile & University | Pensacola | FL | Site Plan = pending Full plans = Pending | Milk | 2025-06-26 08:00 |  | 2026-05-22 08:00 | 2027-04-09 17:00 |  |  |  |  | 2027-04-26 08:00 | 2027-03-31 17:00 | 2027-11-05 17:00 | 2027-11-22 17:00 | 194 | 2027-11-15 | PLACEHOLDER DATES | National Modular | FLPH | FL
RSH-00666 | 4. Due Diligence Phase | 1048 S Pine Ave | Ocala | FL |  |  | 2026-03-25 08:00 |  | 2026-09-04 08:00 | 2027-06-04 17:00 |  |  |  |  | 2027-06-21 08:00 | 2027-08-04 17:00 | 2027-11-19 17:00 | 2027-12-06 17:00 | 152 | 2027-11-29 | PLACEHOLDER DATES |  | FLSW | FL
RSH-00630 | 4. Due Diligence Phase | 201 SW Pine Island Rd | Cape Coral | FL |  |  | 2026-03-11 08:00 |  | 2026-11-20 08:00 | 2027-06-11 17:00 |  |  |  |  | 2027-06-28 08:00 | 2027-08-19 17:00 | 2027-11-19 17:00 | 2027-12-06 17:00 | 145 | 2027-11-29 | PLACEHOLDER DATES |  | FLSW | FL
RSH-00673 | 4. Due Diligence Phase | 16991 Three Oaks Mkt PL | Fort Myers | FL |  |  | 2026-04-08 08:00 |  | 2026-09-11 08:00 | 2027-07-16 17:00 |  |  |  |  | 2027-08-09 08:00 | 2027-09-15 17:00 | 2027-12-17 17:00 | 2028-01-17 17:00 | 131 | 2028-01-10 | PLACEHOLDER DATES |  | FLSW | FL
RSH-00683 | 4. Due Diligence Phase | 3230 W Camp Wisdom Rd | Dallas | TX |  |  | 2026-04-08 08:00 |  | 2026-09-11 08:00 | 2027-07-16 17:00 |  |  |  |  | 2027-08-09 08:00 | 2027-09-15 17:00 | 2027-12-17 17:00 | 2028-01-17 17:00 | 131 | 2028-01-10 | PLACEHOLDER DATES |  | C. TX | Dallas
RSH-00637 | 4. Due Diligence Phase | 2804 Santa Barbara Blvd | Cape Coral | FL | [10 empty] | 2027-07-26 08:00 | 2027-08-25 17:00 | 2027-12-10 17:00 | 2028-01-17 17:00 | #INVALID DATA TYPE | 2028-01-10 |  |  | FLSW | FL